## Study Start-Up Docs
|  | Sponsor Information | [6 empty] | Timeline Information | [11 empty] | Laboratory |  | Consent / IRB Submission and Approval | [11 empty] | Budget and Contract |  |  |  | Sponsor Specific Required Documents | [7 empty] | Almost Done!
Study | PI | Sponsor | Who is contact for start-up - CRO or Sponsor? | CRO | Sponsor/ CRO Contact for Start-Up | Sponsor/ CRO Contact Info | Other Sponsor/ CRO Contact | Other Contact Info | Start-Up Packet (Date Rcd) | Target FPFV (per Sponsor) | Site Contact Form (date sent) | Protocol Signature Page (date sent) | IB Verification Form (date sent) | 1572 (date sent) | Sub-Is on 1572 | CVs (date sent) | Med Licenses (date sent) | Financial Disclosures (date sent) | HSP (date sent) | Sub-I Training (date sent) | CAP / CLIA (date sent) | Normal Ranges (date sent) | Target Date for IRB Submission | Consent Status | Comments on IRB Status | IRB Application Status | IRB Submission Date | IRB Review Date | IRB Review Status | IRB Approval Letter (date sent) | IRB Approved Consent(s) (date sent) | What are the Subject materials? | IRB Approved Stubject Materials (date sent) | IRB Roster/ Compliance (date sent) | Budget Status | Date Budget Final | Contract Status | Date Contracted Executed | Document #1 | Status (date sent) | Document #2 | Status (date sent) | Document #3 | Status (date sent) | Document #4 | Status (date sent) | SIV Date | Site Approved to Enroll (date) | First Pt Scheduled?
BBG-001 | Jayne Smith | BBG | CRO | Quintiles | Amy Monitor | amy@quintiles.com | n/a |  | 2014-09-15 | 2014-12-30 | 2014-10-10 | 2015-02-10 | 2015-02-10 | 2015-02-10 | Baker, Thompson, Davis | sent Smith/Baker/Thomp on 2/10/15: Davis 3/23/15 | Smith/Baker/Thompson 3/23/2015 |  | n/a | scheduled for 4/30/15 | 2015-03-23 | 2015-03-23 | 2015-02-04 | sponsor approved 2/1/15 |  |  | 2015-02-20 | 2015-03-19 | conditional; resubmitted 4/9/15 |  |  | Diary, CFQR, ClinCard (5 docs), IP instructions |  | 2015-03-23 |  |  |  |  | Contact for Transmission of Safety Info
GudDrug4U | Jayne Smith | The Best Company | n/a | n/a | RegDocs: John Doe | john@tbc.com | Contracts/Budgets: Penny Cash | penny@tbc.com | 2015-01-15 | 2015-06-01 | n/a | 2015-03-15 | n/a | 2015-03-15 | Able, Baker Charlie, Davis | all on 4/1/15 | 2015-04-01 | 2015-04-01 | n/a | na | 2015-04-01 | 2015-04-01 | 2015-03-15 | sponsor approved 3/1/15 |  |  | 2015-03-15 | 2015-04-03 |  |  |  | Admin instructions, diary | [6 empty] | Pharmacy Training Form | training scheduled for 4/30/15 | Pharmacy License | sent 3/30/15
The HEALTHY Study | Timothy Davis | TDNCC |  |  | Rachael Buckingham |  | Budget: Lisya |  | 2015-02-20 | 2015-08-20 | 2015-01-15 | 2015-04-13 | n/a | 2015-04-13 | Smith, Baker, Charlie |  |  | n/a |  | n/a | n/a | n/a | 2015-05-15