## Sheet1
This template could be used as a checklist or a GANTT Chart (or as both), as required. The items listed below are not intended to be done sequentially, and some items would be expected to be be completed alongside each other, However the list represents the required steps and procedures that should be completed when setting up a new trial or study. In red is an example of how you might
Procedures/Process Gantt Chart for new trial |  |  | Key Staff | Check Box | Date started | Date Completed | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
[7 empty] | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | wk18 | wk19 | wk20 | wk21 | wk22 | wk23 | wk24
Trial team Holidays/calendar
xxx
xxx
xxx
1.0 Project Initiation (pre-funding) | 1.1 Define the research question | 1.1.1 Identify Principle Investigator (PI) | bar: Month 1 wk1 to Month 1 wk2
1.1.2 Identify co-investigators / potential site PIs | bar: Month 1 wk2 to Month 1 wk4
1.2 Intiate project proposal | bar: Month 1 wk4 to Month 2 wk6
1.3 Pre-trial survey of interest to potential sites | bar: Month 2 wk7 to Month 3 wk9
1.4 Funding proposal / budget submitted | bar: Month 2 wk7 to Month 3 wk10
1.5 Funding secured | bar: Month 3 wk10
1.6 Consider funding needs for sub-studies | bar: Month 3 wk10 to Month 3 wk12
2.0 Funding Secured | 2.1 Identify members of the trial groups | 2.1.1 Establish TMG
2.1.2 Establish the Site TMT
2.1.3 Establish DSMB
2.1.4 Establish TSC if applicable
2.1.4 Establish ERC if applicable
| 2.2 Create Trial Master File (TMF) | 2.2.1 Create the TMF Index
2.2.2 Establish the location for TMF
2.3 Activate the grant
3.0 Trial Set-Up | 3.1 Protocol Development (including the PIS, ICF), Risk Assessment | 3.1.1 Draft Protocol, PIS & ICF
3.1.2 Review of Protocol, PIS, ICF
3.1.3 Submission of protocol, PIS & ICF to TMG
3.1.4 Protocol, PIS & ICF approved for submission to EC and CDSCO, etc.
3.1.5 Commence Risk Assessment & Pharmacovigilance Checklist
3.2 Commence application to CDSCO (for regulatory clinical trial)
3.3 Commence application to Ethics Committee(s)
| 3.4 Commence application to other national regulatory agencies (as applicable) | 3.4.1 HMSC
3.4.2 RCGM
3.4.3 GEAC
3.4.4 NAC-SCRT
3.4.5 Central Drug Testing Laboratories
3.4.6 AERB
3.4.7 DGFT
| 3.5 Trial Registration | 3.5.1 Commence application to CTRI (prospective registration)
3.5.2 ISRCTN
| 3.6 Insurance/Indemnity in place | 3.6.1 Assess for coordinating centre and sites
| 3.7 Identify collaborators and agree upon allocation/delegation of responsibilities | 3.7.1 Sites
3.7.2 Pharmaceutical company (or companies)
3.7.3 Academic Orgnisations
3.7.4 Any other (as applicable)
3.8 Submit applications to CDSCO, EC(s), and other regulatory agencies (if applicable)
| 3.9 CRF and Database Development | 3.9.1 Commence Database Requirement document (user specification document)
3.9.2 Draft CRF (with inputs from STMT and TMG)
3.9.3 Review of CRF
3.9.4 Finalisation of CRF format for circulation to the site(s)
3.9.5 Draft Metadata (with inputs from STMT and TMG)
3.9.6 Review of Metadata
3.9.7 Randomization process defined. Randomization server specification (as applicable).
3.9.8 Database set-up
3.9.9 Database System and Randomization Server User Acceptance Testing
3.9.10 Set-up contact database
3.9.11 Ensure all Database requirements are finalised and signed off
| 3.10 Trial Documentation | 3.10.1 Monitoring Plan
3.10.2 Data Mangement Plan
3.10.3 Safety Management Plan
3.10.4 Commence drafting of SOPs
3.10.5 CRF completion guidelines / manual
3.10.6 Charter and Terms of Reference for TSC / DSMB / TMG signed.
| 3.11 Source or arrange for Trial Supplies (including equipment) | 3.11.1 Manufacture / Import of IP
3.11.2 Labelling the IP
3.11.3 Distribution & storage of IP
3.11.4 Certificate of analysis
3.11.5 Obtain reference information or Investigator's Brochure Summary of Product Characteristics (SmPC)
3.11.6 Other (as applicable)
| 3.12 Agreements with collaborators | 3.12.1 MoU between sponsor and CRO (if applicable)
3.12.2 Clinical Trial Agreement (CTA) between sponsor, site and CRO
3.12 Draft Statistical Analysis Plan
| 3.13 Pharmacovigilance (PV) | 3.14 Draft PV checklist
3.14 Approvals from CDSCO and EC(s) received
4.0 Pre-launch | 4.1 Site Preparedness | 4.1.1 Ensure staff recruitment
| 4.2 Distribution of protocols and CRF to the sites | 4.2.1 ISF set-up with essential documents
| 4.3 Laboratory Set-up | 4.3.1 Laboratory accreditation
4.3.2 Normal range values
4.4 Pharmacy Set-Up
| 4.5 Hold launch meetings / initiation meetings | 4.5.1 Deliver appropriate training to site staff, including Randomization Server (if applicable)
4.5.2 Site Training Logs
4.5.3 Investigators' Meeting
4.5.4 Duty Delegation Logs in place
4.5.5 Ensure all agreements are signed and in order
4.5.6 Ensure all sites have the required finances
4.6 Site Initiated